Climate Action Plan

Comberton Village College
         One year plan: Autumn 2024 – Summer 2025

Your Carbon baseline:  1703 tonnes CO2e         Date:    January 2024

| Decarbonisation and Energy Efficiency: Calculating and taking actions to reduce carbon emissions and becoming more energy efficient |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Cost Input: Low Output: High savings | Ease of implementation (1 easy – 5 difficult) | Timeframe | Key stakeholders | Link to School improvement plan | Progress Track |
| Carbon Calculator: This free digital tool allows you to calculate the carbon footprint for your educational setting. Useful links Count Your carbon | N/A | 3 | January 2025 | Eco Team |  |  |
| Energy – control - Check on Zoned thermostatic control or smart controls on each radiator. Fine tune controls according to need. | N/A | 2 | July 2025 | Site Team |  |  |
| Energy – retrofit - Identify the hot and cold zones in the school and investigate options - Investigate solar providers for maths block roof | N/A TBC | 3 5 | July 2025 July 2025 | Site Team Sustainability Lead |  |  |
| Procurement - Introduce a sustainable procurement policy. - Look at eco friendly photocopy paper - Look at sources of uniform from a sustainability point of view | N/A N/A N/A | 5 4 5 | July 2025 July 2025 July 2025 | Trust Finance / Sustainability Lead ESPO Admin / Trust / Sustainability Lead |  |  |
| Food - Get a more accurate measure of the food’s carbon footprint - Look at ingredient swaps - Become plastic free in the canteen – flavoured water in plastic free carton | N/A N/A N/A | 2 2 3 | December 2024 February 2025 July 2025 | Eco Team Catering / Sustainability Lead / Eco team Catering |  |  |
| Transport - Publish data on carbon footprint of travel to parents / staff - Look at offsetting travel for school trips | N/A Low | 2 5 | July 2025 July 2025 | Sustainability Lead Sustainability Lead / EVC |  |  |
| Waste - Waste audit of other goods such as e-waste - Waste audit - Encourage refillable board pens - Turn unwanted shoes and clothes into book tokens through Recycle to Read (not uniforms) / clothes swap in the sixth form - Look at second hand D of E kit sale - Balance of recycling / general waste bins | N/A N/A N/A N/A N/A N/A | 3 3 2 4 3 3 | July 2025 July 2025 March 2025 July 2025 April 2025 March 2025 | Site / Sustainability Lead / Eco Team Site / Sustainability Lead Sustainability Lead Admin / Sustainability Lead Admin / D of E Site |  |  |

| Adaptation and resilience: Taking actions to reduce the risk of flooding and overheating and to future-proof scarce resources for potential shortages |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Cost | Ease of implementation (1 easy – 5 difficult) | Timeframe | Key stakeholders | Link to School improvement plan | Progress Track |
| Water - Work with Water consultant to identify water saving possibilities. - Let’s Go Guide: Prevent water waste | TBC | 5 | July 2025 | Site / Sustainability Lead |  |  |
| Temperature - Identify key areas that will suffer from extreme heat and look at possible solutions both short term and long term | TBC | 5 | July 2025 | Site / Trust / Sustainability Lead |  |  |

| Biodiversity: Creating habitats and adopting practices that will enhance species diversity on the school estate and beyond |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Cost | Ease of implementation (1 easy – 5 difficult) | Timeframe | Key stakeholders | Link to School improvement plan | Progress Track |
| Nature - Garden waste collection - Tree survey - Do a biodiversity audit of the school site with help from the eco team, Geography, Environmental Science, Wildlife Trust and the local community. This might include birds, insects, plants and trees. - Apply for free hedgerow whips from Tree Council’s Young Tree Champions plus look at opportunities for planting for biodiversity. - Encourage use of National Education Nature Park for lessons and auditing the school site - Research funding for nature regeneration, natural fencing and wetland species reintroduction. - Use Ecosia as default search engine to plant trees with each online search. - Let’s Go Guide: Be bug and bee friendly - Young Tree Champions- Tree Council - NENP weblink - LTL Local School Nature £500 grant -26 Apr, 6 Sept ’24 - PAGES £100-£2,000 grants -3 May ‘24 - Zellar £1000 competition -16 Jun ‘24 - Evolve Get Out £500 grants -early Summer 24 - Ecosia - the search engine that plants trees | N/A N/A N/A N/A N/A N/A N/A | 2 4 4 3 3 4 5 | July 2025 July 2025 July 2025 July 2025 July 2025 July 2025 July 2025 | Site / Contractors Site (Tree info) / Geography / ICT / Eco Team Geography / Eco Team / Science Eco Team Geography / Science Eco Team / Science IT department |  | A level Geography task RSPB schools bird watch completed. Trees ordered and planted. Unable to do on the ipads. |

| Climate education and Green careers: Ensuring the education you provide gives knowledge-rich and comprehensive teaching about climate change, and that your teaching staff feel supported to offer this |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Cost | Ease of implementation (1 easy – 5 difficult) | Timeframe | Key stakeholders | Link to School improvement plan | Progress Track |
| Curriculum - Audit current sustainability content in curriculum with new framework. - Implement Cross Curricular lessons in Curriculum immersions with English, Maths and Science. - Audit the careers programme and look at ways to incorporate green careers into it using the WWF sustainable futures programme. - Share resources to other departments to increase sustainability curriculum content. - CPD for staff e.g. sharing existing sustainability content and developing skills through Carbon Literacy training or climate FRESK. Involve students through Teach the Future. - Create Glossary over climate terminology – check with departments - Teach the Future website. - MoEE curriculum resources - Carbon Literacy | N/A N/A N/A N/A N/A N/A | 2 2 2 2 5 3 | July 2025 October 2024 July 2025 July 2025 July 2025 July 2025 | HODs Maths / English / Science Career Office HODs Assistant Principle Geography / Science |  | Completed In Progress |

Let’s Go Zero contact details:

Email: xxxx@letsgozero.org

Website: letsgozero.org

letsgozero.org

Ashden is registered in England and Wales as a company limited by guarantee.

Registered number: 05062574/ Charity number: 1104153

The Peak, 3rd Floor 5 Wilton Road, London, SW1V 1AP